## How to use
Latest version (click)
Template T04 – Delivery Approach & Tailoring Worksheet
Chooses predictive, agile or hybrid delivery for each workstream, and records which playbook steps to scale up or down.
How to use this template
1. Score each workstream on the eight suitability questions (1 = predictive, 5 = agile).
2. An average of 1–2.4 suggests predictive, 2.5–3.4 hybrid and 3.5–5 agile.
3. Pick a size (Small/Medium/Large) using the tailoring table in the playbook.
4. Record every step you will skip or simplify, with the reason, so auditors and successors understand your choices.
Used in: Step 1.4 – Choose the delivery approach and tailor the playbook
Legend: navy column headers = you fill in; grey headers and cells = calculated automatically; the grey italic row above the headers shows the expected format.
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/).
Version 0.1 (prototype) · October 2026. Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Approach
Delivery approach worksheet | Latest version (click)
Template T04. Score each workstream 1–5 per question. The average suggests an approach; you decide.
Rename the workstream headers (e.g., Software build, Data migration, Training, Procurement).
Suitability question | Workstream 1 | Workstream 2 | Workstream 3 | Workstream 4 | Workstream 5
How clear and stable are the requirements? (1 = clear and fixed, 5 = unclear or expected to change)
How easily can users give frequent feedback? (1 = rarely, 5 = continuously)
How costly is change late in the project? (1 = very costly, 5 = cheap)
Can the work be delivered in small usable increments? (1 = no, 5 = yes)
How experienced is the team with agile practices? (1 = none, 5 = very)
How much regulatory / contractual documentation is required up front? (1 = a lot, 5 = little)
How co-located or collaborative is the team? (1 = dispersed, little overlap, 5 = highly collaborative)
How much does the sponsor need a fixed scope and date? (1 = completely fixed, 5 = flexible)
Average score (auto)
Suggested approach (auto): 1–2.4 Predictive • 2.5–3.4 Hybrid • 3.5–5 Agile
Chosen approach (your decision)

## Tailoring
Tailoring decisions |  | Latest version (click)
Choose Keep / Simplify / Skip for each playbook step and record why. Size guidance: see ‘How to use this playbook’.
Project size:
Step | Playbook step | Phase | Decision | Reason / how simplified
1.1 | Capture the request and build the business case | Initiating
1.2 | Define goals and success criteria | Initiating
1.3 | Identify and analyze stakeholders | Initiating
1.4 | Choose the delivery approach and tailor the playbook | Initiating
1.5 | Draft and approve the project charter | Initiating
1.6 | Hold the initiation gate and kickoff | Initiating
2.1 | Elicit and analyze requirements | Planning
2.2 | Define scope and build the work breakdown structure (WBS) | Planning
2.3 | Build the schedule and milestones | Planning
2.4 | Estimate costs and set the budget | Planning
2.5 | Plan resources, roles and the RACI | Planning
2.6 | Plan risk management: identify, analyze and plan responses | Planning
2.7 | Plan communications and stakeholder engagement | Planning
2.8 | Plan quality and acceptance | Planning
2.9 | Plan sourcing and procurement | Planning
2.10 | Integrate the plan and pass the planning gate | Planning
3.1 | Acquire and onboard the team | Executing
3.2 | Direct the work and run the delivery cadence | Executing
3.3 | Assure quality | Executing
3.4 | Engage stakeholders and communicate | Executing
3.5 | Implement risk responses and resolve issues | Executing
3.6 | Manage vendors and contracts | Executing
3.7 | Manage project knowledge and decisions | Executing
4.1 | Track performance: schedule, cost, scope and quality | Monitoring & Controlling
4.2 | Control changes | Monitoring & Controlling
4.3 | Monitor risks, issues and stakeholder engagement | Monitoring & Controlling
4.4 | Validate scope and accept deliverables | Monitoring & Controlling
4.5 | Report status and escalate | Monitoring & Controlling
5.1 | Confirm final acceptance and transition to operations | Closing
5.2 | Close contracts and finances | Closing
5.3 | Run the retrospective and capture lessons learned | Closing
5.4 | Write the closeout and impact report | Closing
5.5 | Archive, release the team and celebrate | Closing

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve