## How to use
Latest version (click)
Template T08 – WBS & Schedule (Gantt)
Breaks the scope into work packages and schedules them with owners, dates, dependencies and progress.
How to use this template
1. Decompose the deliverables (not activities) until each work package fits in 1–10 working days.
2. Enter the start date and duration. The finish date and the Gantt bars are calculated for you.
3. Use the Predecessor column to record dependencies and to find the critical path.
4. Mark milestones with a duration of 0.
5. Once the plan is approved, copy the dates into the Baseline columns and leave them unchanged.
Used in: Step 2.2 – Define scope and build the work breakdown structure (WBS); Step 2.3 – Build the schedule and milestones; Step 3.2 – Direct the work and run the delivery cadence; Step 4.1 – Track performance: schedule, cost, scope and quality
Legend: navy column headers = you fill in; grey headers and cells = calculated automatically; the grey italic row above the headers shows the expected format.
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/).
This template is also built into the Project Workbook (tab: Schedule).
Version 0.1 (prototype) · October 2026. Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Setup
Project setup | Latest version (click)
Fill in the yellow cells. Everything else in the workbook reads from here. Takes about 5 minutes.
Project name
Organization
Sponsor
Project manager
Product owner / business owner
Project start date
Target finish date
Approved budget ($)
Status date (leave =TODAY() or fix a date) | 2026-10-27
Delivery approach
Project size (tailoring)
Overall status override (optional)
Project summary
Health thresholds (used by the Dashboard)
Schedule: Amber if behind plan by more than (pts) | 5%
Schedule: Red if behind plan by more than (pts) | 15%
Budget: Amber if forecast exceeds approved by more than | 0%
Budget: Red if forecast exceeds approved by more than | 10%
Risk: Amber at this many open Red risks/issues | 1
Risk: Red at this many open Red risks/issues | 3
RAID score at or above which an item is Red | 12
RAID score at or above which an item is Amber | 6
Goals & success criteria (Step 1.2)
Goal / measure | Baseline | Target | Data source | Owner | Current
Core team (Step 3.1)
Name | Project role | Department / company | Allocation | Email / contact

## Schedule
WBS & schedule |  | Latest version (click)
Template T08. Enter tasks top-down by WBS ID. Grey columns calculate automatically. Copy Start/Finish into the Baseline columns once the plan is approved. | [18 empty] | Legend: dark blue = scheduled • light blue = complete • orange = milestone • pink column = status date week
e.g. 2.1 | Requirements workshops | Planning | Product | L. Park | 09/21/2026 | 8 |  | 1.2 | 50% | In progress | 09/21/2026 | 09/30/2026 | [6 empty] | Gantt (weeks starting Monday) →
WBS ID | Task / milestone | Phase | Workstream | Owner | Start | Duration (workdays; 0 = milestone) | Finish (auto) | Predecessor(s) | % complete | Status | Baseline start | Baseline finish | Finish variance (days) (auto) | Planned % by status date (auto) | Flag (auto) | Effective % (auto) | Milestone key (auto) | Weight (auto)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve