## How to use
Latest version (click)
Template T10 – RACI Matrix
Makes clear who is Responsible, Accountable, Consulted and Informed for each deliverable or decision.
How to use this template
1. List the deliverables or decisions down the rows and the roles or people across the columns.
2. Exactly one A per row. The check column flags rows with no A or more than one.
3. Keep the number of C entries low. Each extra one slows decisions down.
4. Review the matrix with the team at kickoff and get explicit agreement on it.
Used in: Step 1.5 – Draft and approve the project charter; Step 2.5 – Plan resources, roles and the RACI; Step 3.1 – Acquire and onboard the team
Legend: navy column headers = you fill in; grey headers and cells = calculated automatically; the grey italic row above the headers shows the expected format.
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/).
This template is also built into the Project Workbook (tab: RACI).
Version 0.1 (prototype) · October 2026. Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## RACI
RACI matrix | Latest version (click)
Template T10. R = Responsible, A = Accountable (exactly one per row), C = Consulted, I = Informed. Rename the role headers (blue row) to fit your team.
e.g. Project charter | A | R | C | C |  | C | C | I
Deliverable / decision | Sponsor | PM | Product Owner | BA | Tech Lead | Security Lead | Finance | Vendor | Role 9 | Role 10 | Check (auto)

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve