## How to use
Latest version (click)
Template T11 – RAID Log (Risks, Assumptions, Issues, Dependencies)
One register for everything that could, or already does, get in the way of delivery.
How to use this template
1. A risk is something that might happen. An issue is something that has happened. Move risks to issues when they occur.
2. Score Probability and Impact 1–5. The score (P×I) and RAG rating are calculated for you.
3. Every Red or Amber item needs an owner, a response (avoid, mitigate, transfer, accept) and a due date.
4. Review the top 10 items in every status meeting and close out stale entries.
Used in: Step 2.6 – Plan risk management: identify, analyze and plan responses; Step 3.3 – Assure quality; Step 3.5 – Implement risk responses and resolve issues; Step 4.3 – Monitor risks, issues and stakeholder engagement
Legend: navy column headers = you fill in; grey headers and cells = calculated automatically; the grey italic row above the headers shows the expected format.
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/).
This template is also built into the Project Workbook (tab: RAID).
Version 0.1 (prototype) · October 2026. Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Setup
Project setup | Latest version (click)
Fill in the yellow cells. Everything else in the workbook reads from here. Takes about 5 minutes.
Project name
Organization
Sponsor
Project manager
Product owner / business owner
Project start date
Target finish date
Approved budget ($)
Status date (leave =TODAY() or fix a date) | 2026-10-27
Delivery approach
Project size (tailoring)
Overall status override (optional)
Project summary
Health thresholds (used by the Dashboard)
Schedule: Amber if behind plan by more than (pts) | 5%
Schedule: Red if behind plan by more than (pts) | 15%
Budget: Amber if forecast exceeds approved by more than | 0%
Budget: Red if forecast exceeds approved by more than | 10%
Risk: Amber at this many open Red risks/issues | 1
Risk: Red at this many open Red risks/issues | 3
RAID score at or above which an item is Red | 12
RAID score at or above which an item is Amber | 6
Goals & success criteria (Step 1.2)
Goal / measure | Baseline | Target | Data source | Owner | Current
Core team (Step 3.1)
Name | Project role | Department / company | Allocation | Email / contact

## RAID
RAID log |  | Latest version (click)
Template T11. Score Probability and Impact 1–5; score, RAG and ID calculate automatically. Review Red/Amber items every week.
| e.g. Risk | CRM API limits | Because of API rate limits, sync may fail, delaying Sprint 4 | Technology | 4 | 4 |  |  | Mitigate | Spike to test limits | T. Becker | 11/20/2026 | Open
ID (auto) | Type | Title | Description (cause → event → impact) | Category | Probability (1–5) | Impact (1–5) | Score (auto) | RAG (auto) | Response | Action / mitigation | Owner | Due | Status | Date raised | Last reviewed | Rank key (auto)

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve