## How to use
Latest version (click)
Template T22 – Go-Live Readiness & Security Checklist
Technical track: confirms that release, security, data, rollback and support criteria are met before production changes.
How to use this template
1. Start the checklist at least two weeks before the planned go-live.
2. Each item needs an owner, a status and evidence (a link or document).
3. Any ‘No’ on a critical item blocks go-live unless the sponsor and Security Lead record an exception.
4. Attach the completed checklist to the CAB request.
Used in: Step 5.1 – Confirm final acceptance and transition to operations
Legend: navy column headers = you fill in; grey headers and cells = calculated automatically; the grey italic row above the headers shows the expected format.
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/).
Version 0.1 (prototype) · October 2026. Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Checklist
Go-live checklist |  | Latest version (click)
Template T22. Status: Yes / No / N/A. Any critical item at ‘No’ means NO-GO unless an exception is recorded. |  |  |  |  | Decision: | NO-GO (16 blocking)
Area | Check | Critical? | Status | Owner | Evidence (link / document) | Exception approved by | Blocks go-live? (auto)
Release | Release scope frozen and release notes written | Yes |  |  |  |  | BLOCKS
Release | All Must requirements accepted (UAT sign-off) | Yes |  |  |  |  | BLOCKS
Release | No open Severity 1/2 defects (or accepted exceptions) | Yes |  |  |  |  | BLOCKS
Release | Deployment runbook rehearsed in a production-like environment | Yes |  |  |  |  | BLOCKS
Release | Rollback plan written and tested | Yes |  |  |  |  | BLOCKS
Release | Change window approved by CAB | Yes |  |  |  |  | BLOCKS
Security | Threat model reviewed and risks treated | Yes |  |  |  |  | BLOCKS
Security | SAST/DAST and dependency scans: no open critical/high findings | Yes |  |  |  |  | BLOCKS
Security | Penetration test findings fixed or formally accepted | Yes |  |  |  |  | BLOCKS
Security | MFA / SSO enforced for admin accounts | Yes |  |  |  |  | BLOCKS
Security | Secrets stored in a vault; no secrets in code | Yes |  |  |  |  | BLOCKS
Security | Logging and audit trail enabled; logs sent to SIEM | No
Data | Data migration rehearsed and reconciled | Yes |  |  |  |  | BLOCKS
Data | Backups configured and a restore tested | Yes |  |  |  |  | BLOCKS
Data | Privacy notice / data processing records updated | No
Operations | Monitoring and alerting configured | Yes |  |  |  |  | BLOCKS
Operations | Support model, on-call and escalation agreed | Yes |  |  |  |  | BLOCKS
Operations | Service desk briefed; knowledge articles published | No
Operations | Hypercare plan and exit criteria agreed | No
People | End users trained / comms sent | No
People | Go/no-go meeting held with sponsor | Yes |  |  |  |  | BLOCKS

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve