## Start Here
Latest version (click)
Project Workbook
Companion to “Project Manager in a Box” – a fill-in-ready tracker with a live dashboard and status report.
Set up in 10 minutes
1. Setup | Enter the project name, dates, budget, sponsor and goals. Leave Status date as =TODAY() or set a fixed reporting date.
2. Schedule | List the phases, tasks and milestones (duration 0) with owners, start dates and durations. Finish dates and the Gantt draw themselves.
3. RAID | Add your top 5–10 risks, assumptions, issues and dependencies with Probability and Impact scores.
4. Budget | Add the budget lines (qty × rate). Enter actuals and forecasts each month.
5. Stakeholders, RACI, Comms | List the key people, who owns what, and how you’ll keep each audience informed.
6. Every week | Update % complete and status, review the RAID log, log changes and decisions, then open the Dashboard and the Status Report.
Legend
Navy column header | You fill these in.
Grey column header / grey cells | Calculated automatically – don’t type over them.
Yellow cells | Inputs on the Setup and Status Report tabs.
Grey italic row above headers | A format example – not part of the data.
Tabs
Dashboard | Live health, KPIs, insights, milestones, top risks, charts.
Status Report | One-page stakeholder update (T15), pre-filled from the Dashboard.
Setup | Project facts, goals, team and health thresholds.
Schedule | WBS, schedule and Gantt (T08).
Requirements | Requirements / backlog (T06).
RAID | Risks, assumptions, issues, dependencies (T11).
Budget | Budget and cost tracking (T09).
Stakeholders | Register and power/interest grid (T03).
RACI | Responsibility matrix (T10).
Comms | Communication plan (T12).
Changes | Change log (T16).
Decisions | Decision log (T17).
Lessons | Retrospective and lessons learned (T19).
Lists | Dropdown values – edit to fit your organization.
License
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/). You may use and adapt this workbook for non-commercial purposes with credit; adaptations must be shared under the same license.
Version
Version 0.1 (prototype) · October 2026 | Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Dashboard
Project dashboard |  |  |  |  | Latest version (click)
PM: – ¦ Sponsor: – ¦ Status date: Oct 27, 2026
[10 empty] | Metric calculations (auto – do not edit) |  | Chart data (auto)
Overall health |  | Work complete |  | Overdue tasks |  | Forecast cost | Open Red risks / issues |  | Pending changes | TotalDur | 0 | Task status | Tasks
Green |  | 0% |  | 0 |  | 0 | 0 |  | 0 | PctComplete | 0% | Not started | 0
Worst of schedule, budget, risk |  | vs 0% planned |  | 0 blocked • 0/0 done |  | vs $0 approved | 0 Amber • 0 open issues |  | 0 approved to date | PctPlanned | 0% | In progress | 0
[10 empty] | SchedVar | 0% | Complete | 0
Health by area | [9 empty] | Overdue | 0 | Blocked | 0
Area | Status | Insight (auto-generated – paste into your status report) | [7 empty] | Blocked | 0 | On hold | 0
Schedule | Green | 0% complete vs 0% planned (0 pts). 0 task(s) overdue, 0 blocked. | [7 empty] | Tasks | 0
Budget | Green | Forecast at completion $0 vs approved $0 (0.0%). Spent to date $0. | [7 empty] | TasksDone | 0 | Budget category | Planned | Forecast (EAC)
Risk | Green | 0 open Red and 0 Amber RAID items; 0 open risks and 0 open issues in total. | [7 empty] | Planned$ | 0 | Labor | 0 | 0
Change | Green | 0 change request(s) awaiting decision. Approved changes to date add 0 days and $0. | [7 empty] | Actual$ | 0 | Vendors & contractors | 0 | 0
Scope |  | 0 of 0 Must-have requirements done or accepted. | [7 empty] | EAC$ | 0 | Software & licenses | 0 | 0
Stakeholders |  | 0 of 0 stakeholders are below their desired engagement level. | [7 empty] | Approved$ | 0 | Hardware | 0 | 0
[10 empty] | BudVarPct | 0% | Training & change | 0 | 0
Earned value (indicative) |  | SPI – • CPI – (below 0.90 needs action; EV = approved budget × % complete) | [7 empty] | RedOpen | 0 | Travel & other | 0 | 0
[10 empty] | AmberOpen | 0 | Contingency reserve | 0 | 0
Next open milestones | [5 empty] | Top 5 open risks & issues (by score) |  |  |  | IssuesOpen | 0
Milestone |  |  | Date | Days |  | Item |  | Score | Owner | RisksOpen | 0 | Open RAID by RAG | Items
[10 empty] | CRPending | 0 | Red | 0
[10 empty] | CRApproved | 0 | Amber | 0
[10 empty] | CRDays | 0 | Green | 0
[10 empty] | CRCost | 0
[10 empty] | StakeGaps | 0
[10 empty] | Stakes | 0
Charts | [9 empty] | Musts | 0
[10 empty] | MustsDone | 0
[10 empty] | RACIErr | 0
[10 empty] | SchedRAG | Green
[10 empty] | BudRAG | Green
[10 empty] | RiskRAG | Green
[10 empty] | CalcRAG | Green
[10 empty] | OverallRAG | Green
[10 empty] | EV | 0
[10 empty] | PV | 0
SPI
CPI
[10 empty] | OpenMS | 0
[10 empty] | DoneMS | 0
Status colors always appear with a text label (Red/Amber/Green) so they are readable without color.

## Status Report
Weekly status report |  | Latest version (click)
Template T15. Grey cells fill in from the Dashboard; complete the yellow cells, then print or copy the page into an email.
Project | 0
Report date | 2026-10-27
Project manager | 0
Sponsor | 0
Overall status | Green
Summary
Health by area
Schedule | Green | 0% complete vs 0% planned (0 pts). 0 task(s) overdue, 0 blocked.
Budget | Green | Forecast at completion $0 vs approved $0 (0.0%). Spent to date $0.
Risk | Green | 0 open Red and 0 Amber RAID items; 0 open risks and 0 open issues in total.
Change | Green | 0 change request(s) awaiting decision. Approved changes to date add 0 days and $0.
Scope |  | 0 of 0 Must-have requirements done or accepted.
Stakeholders |  | 0 of 0 stakeholders are below their desired engagement level.
Completed this period
Planned next period
Decisions / help needed
Ask |  | Owner | Needed by
Top risks & issues
Upcoming milestones

## Setup
Project setup | Latest version (click)
Fill in the yellow cells. Everything else in the workbook reads from here. Takes about 5 minutes.
Project name
Organization
Sponsor
Project manager
Product owner / business owner
Project start date
Target finish date
Approved budget ($)
Status date (leave =TODAY() or fix a date) | 2026-10-27
Delivery approach
Project size (tailoring)
Overall status override (optional)
Project summary
Health thresholds (used by the Dashboard)
Schedule: Amber if behind plan by more than (pts) | 5%
Schedule: Red if behind plan by more than (pts) | 15%
Budget: Amber if forecast exceeds approved by more than | 0%
Budget: Red if forecast exceeds approved by more than | 10%
Risk: Amber at this many open Red risks/issues | 1
Risk: Red at this many open Red risks/issues | 3
RAID score at or above which an item is Red | 12
RAID score at or above which an item is Amber | 6
Goals & success criteria (Step 1.2)
Goal / measure | Baseline | Target | Data source | Owner | Current
Core team (Step 3.1)
Name | Project role | Department / company | Allocation | Email / contact

## Schedule
WBS & schedule |  | Latest version (click)
Template T08. Enter tasks top-down by WBS ID. Grey columns calculate automatically. Copy Start/Finish into the Baseline columns once the plan is approved. | [18 empty] | Legend: dark blue = scheduled • light blue = complete • orange = milestone • pink column = status date week
e.g. 2.1 | Requirements workshops | Planning | Product | L. Park | 09/21/2026 | 8 |  | 1.2 | 50% | In progress | 09/21/2026 | 09/30/2026 | [6 empty] | Gantt (weeks starting Monday) →
WBS ID | Task / milestone | Phase | Workstream | Owner | Start | Duration (workdays; 0 = milestone) | Finish (auto) | Predecessor(s) | % complete | Status | Baseline start | Baseline finish | Finish variance (days) (auto) | Planned % by status date (auto) | Flag (auto) | Effective % (auto) | Milestone key (auto) | Weight (auto)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Requirements
Requirements register |  | Latest version (click)
Template T06. One row per requirement or user story. Every Must needs acceptance criteria before build.
e.g. R-01 | As a volunteer, I can book a shift so that… | Functional | Must | Booking shows instantly; no overbooking | Workshop 1 | P. Shah | 3.2 | Approved | UAT-02
ID | Requirement / user story | Type | Priority | Acceptance criteria | Source | Owner | WBS / epic | Status | Test ref

## RAID
RAID log |  | Latest version (click)
Template T11. Score Probability and Impact 1–5; score, RAG and ID calculate automatically. Review Red/Amber items every week.
| e.g. Risk | CRM API limits | Because of API rate limits, sync may fail, delaying Sprint 4 | Technology | 4 | 4 |  |  | Mitigate | Spike to test limits | T. Becker | 11/20/2026 | Open
ID (auto) | Type | Title | Description (cause → event → impact) | Category | Probability (1–5) | Impact (1–5) | Score (auto) | RAG (auto) | Response | Action / mitigation | Owner | Due | Status | Date raised | Last reviewed | Rank key (auto)

## Budget
Budget & cost tracker |  | Latest version (click)
Template T09. Planned = Qty × Rate. Enter actuals monthly from finance. Variance = Planned − Estimate at completion (negative = overspend). |  |  |  |  | 0 | 0 | Totals → | 0 | 0
e.g. Labor | Business Analyst (internal) | Labor | 400 | 38 |  | 7600 | 8400
Category | Line item | Cost type | Qty / hours | Rate ($) | Planned ($) (auto) | Actual to date ($) | Forecast to complete ($) | Estimate at completion ($) (auto) | Variance ($) (auto) | % spent (auto) | Notes

## Stakeholders
Stakeholder register |  | Latest version (click)
Template T03. Score Power and Interest 1–5. Quadrant: Manage closely (high/high), Keep satisfied (high power), Keep informed (high interest), Monitor.
e.g. Site coordinators | Key users | Operations | 3 | 5 |  | Resistant | Supportive |  | Co-design sessions | Site huddles | P. Shah
Name / group | Role | Organization | Power (1–5) | Interest (1–5) | Grid quadrant (auto) | Current engagement | Desired engagement | Gap? (auto) | Engagement action | Preferred channel | Owner | Notes

## RACI
RACI matrix | Latest version (click)
Template T10. R = Responsible, A = Accountable (exactly one per row), C = Consulted, I = Informed. Rename the role headers (blue row) to fit your team.
e.g. Project charter | A | R | C | C |  | C | C | I
Deliverable / decision | Sponsor | PM | Product Owner | BA | Tech Lead | Security Lead | Finance | Vendor | Role 9 | Role 10 | Check (auto)

## Comms
Communication plan |  | Latest version (click)
Template T12. One row per audience. Put recurring items on the calendar as soon as they are agreed.
e.g. Sponsor | Decisions, risks, progress | Status report | 1:1 + email | Weekly (Mon) | M. Lee | 11/23/2026
Audience | Purpose | Content / format | Channel | Frequency | Owner | Next date | Notes

## Changes
Change log |  |  | Latest version (click)
Template T16. Log every change request, analyze impact, record the decision. Rejected and deferred changes stay in the log.
e.g. CR-001 | 10/22/2026 | A. Grant | Add hardware keys | Supports MFA goal | 0 | 1800 | Low risk | Approve | Approved | D. Ruiz | 10/26/2026 | Yes
CR ID | Date raised | Requested by | Title | Description & reason | Schedule impact (days) | Cost impact ($) | Scope / quality / risk impact | PM recommendation | Decision | Decided by | Decision date | Baselines updated?

## Decisions
Decision log |  |  | Latest version (click)
Template T17. Log decisions that would be costly to reverse or likely to be questioned later.
e.g. DEC-001 | 09/18/2026 | Proceed to Planning | Proceed / defer / buy only | Business case approved | D. Ruiz | Charter
ID | Date | Decision | Options considered | Rationale | Decided by | Related items

## Lessons
Lessons learned |  |  | Latest version (click)
Template T19. Capture lessons as they happen. Every lesson needs a recommendation and an owner.
e.g. L-01 | Planning | Requirements | Continue | On-site workshops surfaced hidden needs | Hold sessions where users work | L. Park | Open
ID | Phase | Category | Start / Stop / Continue | What happened | Recommendation | Owner | Status

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve