## Start Here
Latest version (click)
Project Workbook – Example (Project Beacon)
Companion to “Project Manager in a Box” – a fill-in-ready tracker with a live dashboard and status report.
Set up in 10 minutes
1. Setup | Enter the project name, dates, budget, sponsor and goals. Leave Status date as =TODAY() or set a fixed reporting date.
2. Schedule | List the phases, tasks and milestones (duration 0) with owners, start dates and durations. Finish dates and the Gantt draw themselves.
3. RAID | Add your top 5–10 risks, assumptions, issues and dependencies with Probability and Impact scores.
4. Budget | Add the budget lines (qty × rate). Enter actuals and forecasts each month.
5. Stakeholders, RACI, Comms | List the key people, who owns what, and how you’ll keep each audience informed.
6. Every week | Update % complete and status, review the RAID log, log changes and decisions, then open the Dashboard and the Status Report.
Legend
Navy column header | You fill these in.
Grey column header / grey cells | Calculated automatically – don’t type over them.
Yellow cells | Inputs on the Setup and Status Report tabs.
Grey italic row above headers | A format example – not part of the data.
Tabs
Dashboard | Live health, KPIs, insights, milestones, top risks, charts.
Status Report | One-page stakeholder update (T15), pre-filled from the Dashboard.
Setup | Project facts, goals, team and health thresholds.
Schedule | WBS, schedule and Gantt (T08).
Requirements | Requirements / backlog (T06).
RAID | Risks, assumptions, issues, dependencies (T11).
Budget | Budget and cost tracking (T09).
Stakeholders | Register and power/interest grid (T03).
RACI | Responsibility matrix (T10).
Comms | Communication plan (T12).
Changes | Change log (T16).
Decisions | Decision log (T17).
Lessons | Retrospective and lessons learned (T19).
Lists | Dropdown values – edit to fit your organization.
License
© 2026 James Pearson. “Project Manager in a Box” by James Pearson, licensed under CC BY-NC-SA 4.0 (https://creativecommons.org/licenses/by-nc-sa/4.0/). You may use and adapt this workbook for non-commercial purposes with credit; adaptations must be shared under the same license.
Project Beacon, Northside Food Collective and all people named in this example are fictional.
Version
Version 0.1 (prototype) · October 2026 | Latest version and all files: https://github.com/james-s-pearson/Cybersecurity-Portfolio/tree/main/project-manager-in-a-box

## Dashboard
Project Beacon – Volunteer & Donor Portal |  |  |  |  | Latest version (click)
PM: Marcus Lee ¦ Sponsor: Dana Ruiz, Executive Director ¦ Status date: Jun 22, 2026
[10 empty] | Metric calculations (auto – do not edit) |  | Chart data (auto)
Overall health |  | Work complete |  | Overdue tasks |  | Forecast cost | Open Red risks / issues |  | Pending changes | TotalDur | 137 | Task status | Tasks
Green |  | 100% |  | 0 |  | 169400 | 0 |  | 0 | PctComplete | 100% | Not started | 0
Worst of schedule, budget, risk |  | vs 100% planned |  | 0 blocked • 30/30 done |  | vs $185,000 approved | 1 Amber • 0 open issues |  | 3 approved to date | PctPlanned | 100% | In progress | 0
[10 empty] | SchedVar | 0% | Complete | 30
Health by area | [9 empty] | Overdue | 0 | Blocked | 0
Area | Status | Insight (auto-generated – paste into your status report) | [7 empty] | Blocked | 0 | On hold | 0
Schedule | Green | 100% complete vs 100% planned (0 pts). 0 task(s) overdue, 0 blocked. | [7 empty] | Tasks | 30
Budget | Green | Forecast at completion $169,400 vs approved $185,000 (-8.4%). Spent to date $169,400. | [7 empty] | TasksDone | 30 | Budget category | Planned | Forecast (EAC)
Risk | Green | 0 open Red and 1 Amber RAID items; 3 open risks and 0 open issues in total. | [7 empty] | Planned$ | 184400 | Labor | 44600 | 46600
Change | Green | 0 change request(s) awaiting decision. Approved changes to date add 3 days and $3,800. | [7 empty] | Actual$ | 169400 | Vendors & contractors | 99000 | 99000
Scope | Green | 7 of 7 Must-have requirements done or accepted. | [7 empty] | EAC$ | 169400 | Software & licenses | 12000 | 12000
Stakeholders | Green | 1 of 10 stakeholders are below their desired engagement level. | [7 empty] | Approved$ | 185000 | Hardware | 1800 | 1800
[10 empty] | BudVarPct | -8.432% | Training & change | 8500 | 8500
Earned value (indicative) |  | SPI 1.00 • CPI 1.09 (below 0.90 needs action; EV = approved budget × % complete) | [7 empty] | RedOpen | 0 | Travel & other | 1500 | 1500
[10 empty] | AmberOpen | 1 | Contingency reserve | 17000 | 0
Milestones achieved (latest first) | [5 empty] | Top 5 open risks & issues (by score) |  |  |  | IssuesOpen | 0
Milestone |  |  | Date | Days |  | Item |  | Score | Owner | RisksOpen | 3 | Open RAID by RAG | Items
Closeout approved; project closed |  |  | 2026-06-22 | done |  | R-007 Adoption targets not yet reached at closeout |  | 6 | Priya Shah | CRPending | 0 | Red | 0
Acceptance & transition sign-off (T21) |  |  | 2026-06-12 | done |  | R-008 Phase 2 scope is undecided |  | 4 | Dana Ruiz | CRApproved | 3 | Amber | 1
Go-live |  |  | 2026-06-01 | done |  | R-009 Portal subscription lapses if not renewed |  | 4 | Kevin O’Neil | CRDays | 3 | Green | 2
Go-live readiness & CAB approval |  |  | 2026-05-26 | done | [5 empty] | CRCost | 3800
MVP pilot with 20 volunteers |  |  | 2026-03-27 | done | [5 empty] | StakeGaps | 1
[10 empty] | Stakes | 10
Charts | [9 empty] | Musts | 7
[10 empty] | MustsDone | 7
[10 empty] | RACIErr | 0
[10 empty] | SchedRAG | Green
[10 empty] | BudRAG | Green
[10 empty] | RiskRAG | Green
[10 empty] | CalcRAG | Green
[10 empty] | OverallRAG | Green
[10 empty] | EV | 185000
[10 empty] | PV | 185000
[10 empty] | SPI | 1
[10 empty] | CPI | 1.0921
[10 empty] | OpenMS | 0
[10 empty] | DoneMS | 7
Status colors always appear with a text label (Red/Amber/Green) so they are readable without color.

## Status Report
Weekly status report |  | Latest version (click)
Template T15. Grey cells fill in from the Dashboard; complete the yellow cells, then print or copy the page into an email.
Project | Project Beacon – Volunteer & Donor Portal
Report date | 2026-06-22
Project manager | Marcus Lee
Sponsor | Dana Ruiz, Executive Director
Overall status | Green
Summary
Project Beacon is complete. The portal went live on June 1, 2026, the committed date, and the sponsor approved closeout today. Final cost is $169,400 against $185,000 approved. Adoption is still ramping (61% of shifts booked online against an 80% target), so three follow-up items now belong to the business owners.
Health by area
Schedule | Green | 100% complete vs 100% planned (0 pts). 0 task(s) overdue, 0 blocked.
Budget | Green | Forecast at completion $169,400 vs approved $185,000 (-8.4%). Spent to date $169,400.
Risk | Green | 0 open Red and 1 Amber RAID items; 3 open risks and 0 open issues in total.
Change | Green | 0 change request(s) awaiting decision. Approved changes to date add 3 days and $3,800.
Scope | Green | 7 of 7 Must-have requirements done or accepted.
Stakeholders | Green | 1 of 10 stakeholders are below their desired engagement level.
Completed this period
• Go-live on June 1 after CAB approval on May 26; hypercare finished June 12 with no Severity 1 or 2 incidents
• Acceptance and transition sign-off (T21) signed on June 12
• Retrospective held; lessons recorded (T19); closeout report (T20) approved and records archived
Planned next period
• Business owners take over the three open follow-up items below
• Brightline moves the portal to its standard support plan
• Project team stands down; team members return to their departments
Decisions / help needed
Ask |  | Owner | Needed by
Decide phase 2 scope and funding (gala ticketing, text reminders) |  | Dana Ruiz | 2026-07-31
Re-measure adoption targets and report to the sponsor |  | Priya Shah | 2026-10-30
Renew the portal subscription before the first-year term ends |  | Kevin O’Neil | 2027-05-31
Top risks & issues
R-007 Adoption targets not yet reached at closeout |  |  | Score 6 | Priya Shah
R-008 Phase 2 scope is undecided |  |  | Score 4 | Dana Ruiz
R-009 Portal subscription lapses if not renewed |  |  | Score 4 | Kevin O’Neil
Milestones achieved
Closeout approved; project closed |  |  | 2026-06-22
Acceptance & transition sign-off (T21) |  |  | 2026-06-12
Go-live |  |  | 2026-06-01

## Setup
Project setup | Latest version (click)
Fill in the yellow cells. Everything else in the workbook reads from here. Takes about 5 minutes.
Project name | Project Beacon – Volunteer & Donor Portal
Organization | Northside Food Collective (fictional)
Sponsor | Dana Ruiz, Executive Director
Project manager | Marcus Lee
Product owner / business owner | Priya Shah, Volunteer Programs Manager
Project start date | 2025-12-29
Target finish date | 2026-06-26
Approved budget ($) | 185000
Status date (leave =TODAY() or fix a date) | 2026-06-22
Delivery approach | Hybrid
Project size (tailoring) | Medium
Overall status override (optional)
Project summary | Replace spreadsheets and paper sign-up sheets with a secure online portal where volunteers register, book shifts and log hours, and donors manage recurring gifts. The portal integrates with the existing donor CRM. Delivered and closed; see the Status Report and the Lessons tab.
Health thresholds (used by the Dashboard)
Schedule: Amber if behind plan by more than (pts) | 5%
Schedule: Red if behind plan by more than (pts) | 15%
Budget: Amber if forecast exceeds approved by more than | 0%
Budget: Red if forecast exceeds approved by more than | 10%
Risk: Amber at this many open Red risks/issues | 1
Risk: Red at this many open Red risks/issues | 3
RAID score at or above which an item is Red | 12
RAID score at or above which an item is Amber | 6
Goals & success criteria (Step 1.2)
Goal / measure | Baseline | Target | Data source | Owner | Current
Volunteer shifts booked online | 0% | 80% of shifts | Portal reports | Priya Shah | 61% (still rising)
Staff hours spent on scheduling | 22 hrs/week | ≤ 8 hrs/week | Time study | Priya Shah | 11 hrs/week
Recurring donors | 310 | 400 by Oct 2026 | Donor CRM | Rosa Delgado | 327
Admin accounts using MFA | 0% | 100% at go-live | Identity provider report | Aisha Grant | 100%
Core team (Step 3.1)
Name | Project role | Department / company | Allocation | Email / contact
Dana Ruiz | Sponsor | Executive Director | 10%
Marcus Lee | Project Manager | Operations | 60%
Priya Shah | Product Owner | Volunteer Programs | 30%
Lena Park | Business Analyst | Operations | 50%
Tom Becker | Technical Lead | Brightline Software (vendor) | 100%
Aisha Grant | Security Lead | IT | 20%
Kevin O’Neil | Finance Partner | Finance | 5%
Rosa Delgado | Donor Relations Lead | Development | 15%

## Schedule
WBS & schedule |  | Latest version (click)
Template T08. Enter tasks top-down by WBS ID. Grey columns calculate automatically. Copy Start/Finish into the Baseline columns once the plan is approved. | [18 empty] | Legend: dark blue = scheduled • light blue = complete • orange = milestone • pink column = status date week
e.g. 2.1 | Requirements workshops | Planning | Product | L. Park | 09/21/2026 | 8 |  | 1.2 | 50% | In progress | 09/21/2026 | 09/30/2026 | [6 empty] | Gantt (weeks starting Monday) →
WBS ID | Task / milestone | Phase | Workstream | Owner | Start | Duration (workdays; 0 = milestone) | Finish (auto) | Predecessor(s) | % complete | Status | Baseline start | Baseline finish | Finish variance (days) (auto) | Planned % by status date (auto) | Flag (auto) | Effective % (auto) | Milestone key (auto) | Weight (auto) | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
1 | Initiating | Initiating | Governance | Marcus Lee | 2025-12-29 | 10 | 2026-01-09 |  | 100% | Complete | 2025-12-29 | 2026-01-09 | 0 | 100% |  | 100% |  | 0
1.1 | Intake & business case approved | Initiating | Governance | Marcus Lee | 2025-12-29 | 5 | 2026-01-02 |  | 100% | Complete | 2025-12-29 | 2026-01-02 | 0 | 100% |  | 100% |  | 5
1.2 | Charter signed | Initiating | Governance | Dana Ruiz | 2026-01-09 | 0 | 2026-01-09 | 1.1 | 100% | Complete | 2026-01-09 | 2026-01-09 | 0 | 100% |  | 100% | -46031.0001 | 0
2 | Planning | Planning | Governance | Marcus Lee | 2026-01-12 | 20 | 2026-02-06 | 1.2 | 100% | Complete | 2026-01-12 | 2026-02-06 | 0 | 100% |  | 100% |  | 0
2.1 | Requirements workshops | Planning | Product | Lena Park | 2026-01-12 | 8 | 2026-01-21 | 1.2 | 100% | Complete | 2026-01-12 | 2026-01-21 | 0 | 100% |  | 100% |  | 8
2.2 | Vendor selected & SOW signed | Planning | Procurement | Marcus Lee | 2026-01-19 | 10 | 2026-01-30 | 2.1 | 100% | Complete | 2026-01-19 | 2026-01-30 | 0 | 100% |  | 100% |  | 10
2.3 | Security requirements & threat model | Planning | Security | Aisha Grant | 2026-01-26 | 5 | 2026-01-30 | 2.1 | 100% | Complete | 2026-01-26 | 2026-01-30 | 0 | 100% |  | 100% |  | 5
2.4 | Plan & baselines approved (gate) | Planning | Governance | Dana Ruiz | 2026-02-06 | 0 | 2026-02-06 | 2.2,2.3 | 100% | Complete | 2026-02-06 | 2026-02-06 | 0 | 100% |  | 100% | -46059.0001 | 0
3 | Build & configure (sprints) | Executing | Product | Tom Becker | 2026-02-09 | 55 | 2026-04-24 | 2.4 | 100% | Complete | 2026-02-09 | 2026-04-24 | 0 | 100% |  | 100% |  | 0
3.1 | Sprint 1 – Volunteer registration | Executing | Product | Tom Becker | 2026-02-09 | 10 | 2026-02-20 | 2.4 | 100% | Complete | 2026-02-09 | 2026-02-20 | 0 | 100% |  | 100% |  | 10
3.2 | Sprint 2 – Shift booking | Executing | Product | Tom Becker | 2026-02-23 | 10 | 2026-03-06 | 3.1 | 100% | Complete | 2026-02-23 | 2026-03-06 | 0 | 100% |  | 100% |  | 10
3.3 | Sprint 3 – Hours logging & reports | Executing | Product | Tom Becker | 2026-03-09 | 10 | 2026-03-20 | 3.2 | 100% | Complete | 2026-03-09 | 2026-03-20 | 0 | 100% |  | 100% |  | 10
3.4 | Sprint 4 – Donor CRM integration | Executing | Integration | Tom Becker | 2026-03-30 | 10 | 2026-04-10 | 3.3 | 100% | Complete | 2026-03-23 | 2026-04-03 | 7 | 100% |  | 100% |  | 10
3.5 | Sprint 5 – Recurring giving | Executing | Product | Tom Becker | 2026-04-13 | 10 | 2026-04-24 | 3.4 | 100% | Complete | 2026-04-06 | 2026-04-17 | 7 | 100% |  | 100% |  | 10
3.6 | MVP pilot with 20 volunteers | Executing | Product | Priya Shah | 2026-03-27 | 0 | 2026-03-27 | 3.3 | 100% | Complete | 2026-03-27 | 2026-03-27 | 0 | 100% |  | 100% | -46108.0002 | 0
4 | Security & quality | Executing | Security | Aisha Grant | 2026-02-23 | 65 | 2026-05-22 |  | 100% | Complete | 2026-02-23 | 2026-05-22 | 0 | 100% |  | 100% |  | 0
4.1 | SSO + MFA configuration | Executing | Security | Aisha Grant | 2026-02-23 | 8 | 2026-03-04 | 2.3 | 100% | Complete | 2026-02-23 | 2026-03-04 | 0 | 100% |  | 100% |  | 8
4.2 | Data migration from spreadsheets | Executing | Integration | Lena Park | 2026-03-02 | 15 | 2026-03-20 | 3.1 | 100% | Complete | 2026-02-23 | 2026-03-13 | 7 | 100% |  | 100% |  | 15
4.3 | Penetration test (third party) | Executing | Security | Aisha Grant | 2026-05-04 | 5 | 2026-05-08 | 3.5 | 100% | Complete | 2026-04-27 | 2026-05-01 | 7 | 100% |  | 100% |  | 5
4.4 | User acceptance testing | Monitoring & Controlling | Product | Priya Shah | 2026-05-11 | 10 | 2026-05-22 | 4.3 | 100% | Complete | 2026-05-04 | 2026-05-15 | 7 | 100% |  | 100% |  | 10
5 | Launch, transition & closeout | Closing | Operations | Marcus Lee | 2026-05-26 | 20 | 2026-06-22 |  | 100% | Complete | 2026-05-19 | 2026-06-15 | 7 | 100% |  | 100% |  | 0
5.1 | Go-live readiness & CAB approval | Closing | Operations | Aisha Grant | 2026-05-26 | 0 | 2026-05-26 | 4.4 | 100% | Complete | 2026-05-19 | 2026-05-19 | 7 | 100% |  | 100% | -46168.0003 | 0
5.2 | Volunteer & staff training | Closing | Change | Rosa Delgado | 2026-05-26 | 4 | 2026-05-29 | 4.4 | 100% | Complete | 2026-05-19 | 2026-05-22 | 7 | 100% |  | 100% |  | 4
5.3 | Go-live | Closing | Operations | Tom Becker | 2026-06-01 | 0 | 2026-06-01 | 5.1 | 100% | Complete | 2026-05-25 | 2026-05-25 | 7 | 100% |  | 100% | -46174.0003 | 0
5.4 | Hypercare (2 weeks) | Closing | Operations | Tom Becker | 2026-06-01 | 10 | 2026-06-12 | 5.3 | 100% | Complete | 2026-05-25 | 2026-06-05 | 7 | 100% |  | 100% |  | 10
5.5 | Acceptance & transition sign-off (T21) | Closing | Governance | Priya Shah | 2026-06-12 | 0 | 2026-06-12 | 5.4 | 100% | Complete | 2026-06-05 | 2026-06-05 | 7 | 100% |  | 100% | -46185.0003 | 0
5.6 | Retrospective & lessons learned (T19) | Closing | Governance | Marcus Lee | 2026-06-15 | 1 | 2026-06-15 | 5.5 | 100% | Complete | 2026-06-08 | 2026-06-08 | 7 | 100% |  | 100% |  | 1
5.7 | Contract & finance closure | Closing | Procurement | Kevin O’Neil | 2026-06-15 | 3 | 2026-06-17 | 5.5 | 100% | Complete | 2026-06-08 | 2026-06-10 | 7 | 100% |  | 100% |  | 3
5.8 | Closeout report (T20) & records archived | Closing | Governance | Marcus Lee | 2026-06-16 | 3 | 2026-06-18 | 5.6 | 100% | Complete | 2026-06-09 | 2026-06-11 | 7 | 100% |  | 100% |  | 3
5.9 | Closeout approved; project closed | Closing | Governance | Dana Ruiz | 2026-06-22 | 0 | 2026-06-22 | 5.8 | 100% | Complete | 2026-06-15 | 2026-06-15 | 7 | 100% |  | 100% | -46195.0003 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Requirements
Requirements register |  | Latest version (click)
Template T06. One row per requirement or user story. Every Must needs acceptance criteria before build.
e.g. R-01 | As a volunteer, I can book a shift so that… | Functional | Must | Booking shows instantly; no overbooking | Workshop 1 | P. Shah | 3.2 | Approved | UAT-02
ID | Requirement / user story | Type | Priority | Acceptance criteria | Source | Owner | WBS / epic | Status | Test ref
R-01 | As a volunteer, I can create an account and sign in with email + MFA | Functional | Must | Account created in < 3 min; MFA enrolment enforced | Workshop 1 | Priya Shah | 3.1 | Accepted | UAT-01
R-02 | As a volunteer, I can see open shifts and book or cancel one | Functional | Must | Booking reflected instantly; cancel up to 24h before | Workshop 1 | Priya Shah | 3.2 | Accepted | UAT-02
R-03 | As a coordinator, I can create recurring shifts with capacity limits | Functional | Must | No overbooking above capacity | Workshop 2 | Priya Shah | 3.2 | Accepted | UAT-03
R-04 | As a volunteer, I can log hours and download a certificate | Functional | Should | PDF certificate shows total hours | Survey | Priya Shah | 3.3 | Accepted | UAT-04
R-05 | As a donor, I can set up and change a recurring gift | Functional | Must | Payment handled by PCI-compliant processor; no card data stored | Development team | Rosa Delgado | 3.5 | Accepted | UAT-05
R-06 | Volunteer and donor records sync with the donor CRM nightly | Functional | Must | Sync errors alerted to IT within 1h | IT | Tom Becker | 3.4 | Accepted | SIT-01
R-07 | Portal meets WCAG 2.2 AA | Non-functional | Must | Zero critical accessibility findings | Policy | Lena Park | 4.4 | Accepted | ACC-01
R-08 | Personal data encrypted in transit and at rest | Non-functional | Must | TLS 1.2+; AES-256 at rest | Security | Aisha Grant | 4.1 | Accepted | SEC-01
R-09 | Pages load in under 2 seconds for 95% of requests | Non-functional | Should | Load test at 300 concurrent users | IT | Tom Becker | 4.4 | Accepted | PERF-01
R-10 | Text-message shift reminders | Functional | Could | Opt-in only | Survey | Priya Shah | Phase 2 | Deferred | n/a

## RAID
RAID log |  | Latest version (click)
Template T11. Score Probability and Impact 1–5; score, RAG and ID calculate automatically. Review Red/Amber items every week.
| e.g. Risk | CRM API limits | Because of API rate limits, sync may fail, delaying Sprint 4 | Technology | 4 | 4 |  |  | Mitigate | Spike to test limits | T. Becker | 11/20/2026 | Open
ID (auto) | Type | Title | Description (cause → event → impact) | Category | Probability (1–5) | Impact (1–5) | Score (auto) | RAG (auto) | Response | Action / mitigation | Owner | Due | Status | Date raised | Last reviewed | Rank key (auto)
R-001 | Risk | Volunteer adoption lower than target | Because many volunteers are older and used to paper sign-ups, adoption may lag, reducing staff-time savings. | Change adoption | 2 | 4 | 8 | Amber | Mitigate | Pilot with 20 volunteers (Mar 27); paper-to-portal help desk at pantry sites. Done: 61% of shifts booked online three weeks after go-live. | Priya Shah | 2026-03-27 | Closed | 2026-01-16
R-002 | Risk | CRM integration more complex than estimated | Because the CRM API has rate limits, sync may need redesign, delaying Sprint 4. | Technology | 4 | 4 | 16 | Red | Mitigate | Spike in Sprint 2 to test API limits; vendor architect review. Done: batch size reduced; sync stays within limits. | Tom Becker | 2026-03-13 | Closed | 2026-01-23
I-001 | Issue | Spreadsheet data quality blocks migration | Duplicate and incomplete volunteer records (approx. 18%) are blocking the migration script. | Data | 5 | 3 | 15 | Red | Mitigate | Two temps cleaned the data (CR-003); dedupe rules agreed with the PO. Done: migration completed Mar 20. | Lena Park | 2026-03-20 | Closed | 2026-03-02
R-003 | Risk | Penetration test finds high-severity issues late | Because the pen test is scheduled close to UAT, fixes could push go-live. | Security | 2 | 5 | 10 | Amber | Mitigate | Automated DAST each sprint; pen-test retest slot booked. Done: one high finding fixed and retested before UAT. | Aisha Grant | 2026-04-27 | Closed | 2026-01-26
R-004 | Risk | Vendor key developer unavailable in the holiday period | Leave may reduce vendor capacity during Sprints 4–5. | Resources | 3 | 3 | 9 | Amber | Mitigate | Vendor confirmed a backup developer in writing. Done: Sprints 4 and 5 staffed. | Marcus Lee | 2026-03-09 | Closed | 2026-01-13
R-005 | Risk | Donation processor fees increase | Fee changes could reduce net donation value. | Finance | 2 | 2 | 4 | Green | Accept | Monitored at steering; no change in fees during the project. | Kevin O’Neil | 2026-04-24 | Closed | 2026-01-13
A-001 | Assumption | Volunteers have a mobile phone for MFA | Assumes at least 90% of volunteers can use an authenticator or SMS. | Security | 2 | 3 | 6 | Amber | Mitigate | Hardware keys offered at pantry sites (CR-001). Confirmed: 96% used a phone; 60 keys issued. | Aisha Grant | 2026-03-27 | Closed | 2026-01-16
D-001 | Dependency | CRM vendor sandbox access | Sprint 4 depends on CRM vendor providing a sandbox. | Vendors | 3 | 3 | 9 | Amber | Mitigate | Request escalated through the vendor account manager. Sandbox arrived Mar 25, a week late; Sprint 4 started Mar 30. | Tom Becker | 2026-03-18 | Closed | 2026-01-13
R-006 | Risk | Scope creep from event registration requests | Development team wants gala ticketing added. | Scope | 3 | 3 | 9 | Amber | Avoid | Logged as CR-002; deferred to phase 2. | Marcus Lee | 2026-02-23 | Closed | 2026-02-18
R-007 | Risk | Adoption targets not yet reached at closeout | Because adoption is still ramping, shift booking (61% vs 80%) and scheduling hours (11 vs 8 a week) may take longer to reach target, delaying the staff-time savings. | Change adoption | 3 | 2 | 6 | Amber | Transfer | Handed to the business owner at closeout. Re-measure both targets and the donor count on Oct 30, 2026 and report to the sponsor in November. | Priya Shah | 2026-10-30 | Open | 2026-06-18 |  | 6.0986
R-008 | Risk | Phase 2 scope is undecided | Gala ticketing (CR-002) and text reminders (R-10) were deferred. Without a decision, requests will keep arriving with no owner. | Scope | 2 | 2 | 4 | Green | Transfer | Handed to the sponsor. Decide phase 2 scope and funding. | Dana Ruiz | 2026-07-31 | Open | 2026-06-18 |  | 4.0985
R-009 | Risk | Portal subscription lapses if not renewed | The year-1 platform subscription was paid at go-live and ends on May 31, 2027. A lapse would take the portal offline. | Finance | 1 | 4 | 4 | Green | Transfer | Handed to Finance. Renew before the term ends. | Kevin O’Neil | 2027-05-31 | Open | 2026-06-18 |  | 4.0984

## Budget
Budget & cost tracker |  | Latest version (click)
Template T09. Planned = Qty × Rate. Enter actuals monthly from finance. Variance = Planned − Estimate at completion (negative = overspend). |  |  |  |  | 184400 | 169400 | Totals → | 169400 | 15000
e.g. Labor | Business Analyst (internal) | Labor | 400 | 38 |  | 7600 | 8400
Category | Line item | Cost type | Qty / hours | Rate ($) | Planned ($) (auto) | Actual to date ($) | Forecast to complete ($) | Estimate at completion ($) (auto) | Variance ($) (auto) | % spent (auto) | Notes
Vendors & contractors | Brightline build – 5 sprints | Non-labor | 5 | 18000 | 90000 | 90000 | 0 | 90000 | 0 | 100% | Fixed price per sprint. Final invoice paid Jun 17.
Vendors & contractors | Penetration test | Non-labor | 1 | 9000 | 9000 | 9000 | 0 | 9000 | 0 | 100% | Includes the retest of one high-severity finding.
Labor | Project Manager (internal) | Labor | 520 | 45 | 23400 | 23400 | 0 | 23400 | 0 | 100%
Labor | Business Analyst (internal) | Labor | 400 | 38 | 15200 | 16000 | 0 | 16000 | -800 | 105.3% | +$800 (21 extra hours for UAT script rework), approved as CR-004.
Labor | Data cleanup temps | Labor | 240 | 25 | 6000 | 7200 | 0 | 7200 | -1200 | 120% | +$1,200 (48 extra hours), approved as CR-003.
Software & licenses | Portal platform subscription (yr 1) | Non-labor | 12 | 650 | 7800 | 7800 | 0 | 7800 | 0 | 100% | Paid in advance at go-live. Renewal due May 31, 2027 (Kevin O’Neil).
Software & licenses | Identity provider / MFA licenses | Non-labor | 1 | 4200 | 4200 | 4200 | 0 | 4200 | 0 | 100%
Hardware | Hardware security keys (pantry sites) | Non-labor | 60 | 30 | 1800 | 1800 | 0 | 1800 | 0 | 100% | Added by CR-001.
Training & change | Training materials & sessions | Non-labor | 1 | 6000 | 6000 | 6000 | 0 | 6000 | 0 | 100%
Training & change | Pantry help-desk volunteers stipend | Non-labor | 1 | 2500 | 2500 | 2500 | 0 | 2500 | 0 | 100%
Travel & other | Site visits & printing | Non-labor | 1 | 1500 | 1500 | 1500 | 0 | 1500 | 0 | 100%
Contingency reserve | Risk reserve (~10%) | Reserve | 1 | 17000 | 17000 | 0 | 0 | 0 | 17000 | 0% | Closed out. The $2,000 drawn (CR-003, CR-004) is shown on the lines it paid for; $15,000 was not needed.

## Stakeholders
Stakeholder register |  | Latest version (click)
Template T03. Score Power and Interest 1–5. Quadrant: Manage closely (high/high), Keep satisfied (high power), Keep informed (high interest), Monitor.
e.g. Site coordinators | Key users | Operations | 3 | 5 |  | Resistant | Supportive |  | Co-design sessions | Site huddles | P. Shah
Name / group | Role | Organization | Power (1–5) | Interest (1–5) | Grid quadrant (auto) | Current engagement | Desired engagement | Gap? (auto) | Engagement action | Preferred channel | Owner | Notes
Dana Ruiz | Executive Director (Sponsor) | Leadership | 5 | 5 | Manage closely | Leading | Leading | OK | Weekly 1:1; steering chair | 1:1 + status email | Marcus Lee
Board Technology Committee | Oversight | Board | 5 | 3 | Manage closely | Supportive | Supportive | OK | Monthly briefing with demo; final results memo | Monthly memo | Dana Ruiz
Priya Shah | Product Owner | Volunteer Programs | 4 | 5 | Manage closely | Leading | Leading | OK | Sprint reviews; backlog refinement | Slack + meetings | Marcus Lee
Pantry site coordinators | Key users | Operations | 3 | 5 | Manage closely | Supportive | Supportive | OK | Co-design sessions; pilot champions at each site; thank-you huddle after hypercare | Site huddles | Priya Shah
Volunteers (approx. 1,200) | End users | Community | 2 | 4 | Keep informed | Neutral | Supportive | Gap | Newsletter teasers; pilot; how-to videos; follow-up survey in October | Email + SMS | Rosa Delgado
Rosa Delgado | Donor Relations Lead | Development | 3 | 4 | Manage closely | Supportive | Supportive | OK | Include in Sprint 5 reviews | Teams | Marcus Lee
Aisha Grant | IT Manager / Security Lead | IT | 4 | 4 | Manage closely | Leading | Leading | OK | Security gate owner; CAB sponsor | Teams | Marcus Lee
Kevin O’Neil | Finance Partner | Finance | 3 | 2 | Keep satisfied | Supportive | Supportive | OK | Monthly budget review | Email | Marcus Lee
Brightline Software | Implementation vendor | Vendor | 3 | 5 | Manage closely | Supportive | Supportive | OK | Weekly vendor check-in | Weekly call | Marcus Lee
CRM vendor | Integration dependency | Vendor | 2 | 2 | Monitor | Supportive | Supportive | OK | Escalate sandbox request via account manager | Email | Tom Becker

## RACI
RACI matrix | Latest version (click)
Template T10. R = Responsible, A = Accountable (exactly one per row), C = Consulted, I = Informed. Rename the role headers (blue row) to fit your team.
e.g. Project charter | A | R | C | C |  | C | C | I
Deliverable / decision | Sponsor | PM | Product Owner | BA | Tech Lead | Security Lead | Finance | Vendor | Role 9 | Role 10 | Check (auto)
Project charter | A | R | C | C |  | C | C |  |  |  | OK
Requirements / backlog | I | C | A | R | C | C |  | C |  |  | OK
Schedule & milestones | I | A | C | C | C | C |  | C |  |  | OK
Budget | A | R | I |  |  |  | C | I |  |  | OK
Solution design | I | C | C | C | A | C |  | R |  |  | OK
Security sign-off | I | I | C |  | C | A |  | R |  |  | OK
UAT & acceptance | I | C | A | R | C | C |  | C |  |  | OK
Go-live decision | A | R | C |  | C | C |  | C |  |  | OK
Training & adoption | I | A | R | C |  |  |  | C |  |  | OK

## Comms
Communication plan |  | Latest version (click)
Template T12. One row per audience. Put recurring items on the calendar as soon as they are agreed.
e.g. Sponsor | Decisions, risks, progress | Status report | 1:1 + email | Weekly (Mon) | M. Lee | 11/23/2026
Audience | Purpose | Content / format | Channel | Frequency | Owner | Next date | Notes
Sponsor | Decisions, risks, progress | Final status report + closeout report | 1:1 + email | Weekly (Mon) | Marcus Lee | 2026-06-22
Steering committee | Gate decisions, budget, escalations | Closeout pack + dashboard | Meeting | Monthly | Marcus Lee | 2026-06-22
Board Technology Committee | Oversight, confidence | Final 1-page memo + results | Email | Monthly | Dana Ruiz | 2026-07-14
Delivery team | Coordination, blockers | Stand-up; sprint ceremonies; retrospective | Teams / in person | Daily + per sprint | Tom Becker | 2026-06-22
Site coordinators | Readiness, feedback | Thank-you huddle + results | Site huddle | Bi-weekly | Priya Shah | 2026-06-24
Volunteers | Awareness, training | Newsletter: portal results and how to get help | Email + SMS | Monthly; weekly near launch | Rosa Delgado | 2026-07-01
IT / CAB | Change approval | Post-implementation review | Ticket | Before go-live | Aisha Grant | 2026-07-07

## Changes
Change log |  |  | Latest version (click)
Template T16. Log every change request, analyze impact, record the decision. Rejected and deferred changes stay in the log.
e.g. CR-001 | 10/22/2026 | A. Grant | Add hardware keys | Supports MFA goal | 0 | 1800 | Low risk | Approve | Approved | D. Ruiz | 10/26/2026 | Yes
CR ID | Date raised | Requested by | Title | Description & reason | Schedule impact (days) | Cost impact ($) | Scope / quality / risk impact | PM recommendation | Decision | Decided by | Decision date | Baselines updated?
CR-001 | 2026-02-12 | Aisha Grant | Add hardware security keys for volunteers without phones | Supports the 100% MFA goal; resolves the MFA assumption | 0 | 1800 | Low risk; procurement lead time 2 weeks | Approve | Approved | Dana Ruiz | 2026-02-17 | Yes
CR-002 | 2026-02-18 | Rosa Delgado | Add gala event ticketing | Development team request for spring gala | 15 | 22000 | New payment flows; adds PCI scope | Defer to phase 2 | Deferred | Dana Ruiz | 2026-02-23 | No
CR-003 | 2026-03-05 | Lena Park | Extend data cleanup by 48 temp hours | Resolves migration blocker (issue in RAID); 48 hours at $25 | 3 | 1200 | Uses contingency reserve; above the PM’s $1,000 limit | Approve | Approved | Dana Ruiz | 2026-03-11 | Yes
CR-004 | 2026-04-24 | Lena Park | Add 21 business-analyst hours for UAT script rework | Test scripts needed rework after the sprint 5 changes | 0 | 800 | No milestone change; within the PM’s $1,000 limit | Approve | Approved | Marcus Lee | 2026-04-27 | Yes

## Decisions
Decision log |  |  | Latest version (click)
Template T17. Log decisions that would be costly to reverse or likely to be questioned later.
e.g. DEC-001 | 09/18/2026 | Proceed to Planning | Proceed / defer / buy only | Business case approved | D. Ruiz | Charter
ID | Date | Decision | Options considered | Rationale | Decided by | Related items
DEC-001 | 2026-01-09 | Proceed with Project Beacon (initiation gate) | Proceed / defer to FY28 / buy off-the-shelf only | Business case shows staff-time savings of approx. 14 hrs/week; grant funding available | Dana Ruiz | Charter
DEC-002 | 2026-01-30 | Select Brightline Software as build vendor | 3 bids scored on cost, nonprofit experience, security | Highest score (82/100); SOC 2 Type II report reviewed | Dana Ruiz | SOW-01
DEC-003 | 2026-02-06 | Hybrid delivery: 2-week sprints within fixed milestone plan | Predictive / Agile / Hybrid | Fixed grant deadline + evolving requirements | Marcus Lee | T04 worksheet
DEC-004 | 2026-02-23 | Defer gala ticketing to phase 2 | Add now / defer / reject | Would add 15 days and PCI scope | Dana Ruiz | CR-002
DEC-005 | 2026-03-11 | Pay for extra data-cleanup hours from the contingency reserve | Fund from reserve / delay migration / accept 18% bad records | Migration was the blocker for Sprint 4; $1,200 is within the reserve and the sponsor’s authority | Dana Ruiz | CR-003
DEC-006 | 2026-05-26 | Go live on June 1 | Go on June 1 / delay one week | CAB approved; no Severity 1 or 2 defects open; training complete; rollback plan tested | Dana Ruiz | 5.1, T22
DEC-007 | 2026-06-12 | Accept the portal and hand it over to operations | Accept / extend hypercare / accept with conditions | Two weeks of hypercare with no Severity 1 or 2 incidents; runbook and support contacts handed over | Dana Ruiz | T21

## Lessons
Lessons learned |  |  | Latest version (click)
Template T19. Capture lessons as they happen. Every lesson needs a recommendation and an owner.
e.g. L-01 | Planning | Requirements | Continue | On-site workshops surfaced hidden needs | Hold sessions where users work | L. Park | Open
ID | Phase | Category | Start / Stop / Continue | What happened | Recommendation | Owner | Status
L-01 | Planning | Requirements | Continue | Workshops at pantry sites surfaced needs that office meetings missed | Hold requirements sessions where users work | Lena Park | Actioned
L-02 | Executing | Data | Start | Spreadsheet data quality was assumed, not checked, and blocked migration for two weeks | Profile source data during Planning (add to the WBS template) | Marcus Lee | Actioned
L-03 | Executing | Vendors | Continue | Sprint reviews with the vendor kept progress visible | Keep the vendor in all ceremonies; write attendance into the SOW | Marcus Lee | Actioned
L-04 | Executing | Vendors | Start | The CRM sandbox arrived 8 working days late and pushed Sprint 4 back a week | Name third-party access in the SOW and request it at kickoff, with a needed-by date | Tom Becker | Open
L-05 | Planning | Schedule | Continue | A one-week buffer between the team’s plan and the committed go-live date absorbed the Sprint 4 slip | Keep a visible buffer between the internal plan and any date promised outside the team | Marcus Lee | Open
L-06 | Closing | Change | Start | The 80% adoption target was set before any pilot data existed and was not reached by closeout | Set adoption targets after the pilot, and name the post-launch owner in the charter | Priya Shah | Open

## Lists
Dropdown lists |  | Latest version (click)
Edit these lists to match your organization. Dropdowns across the workbook update automatically.
Status | Phase | RAIDType | Response | OpenClosed | RAG | MoSCoW | ReqType | ReqStatus | Eng | CRDecision | SSC | YesNo | Approach | Size | BudgetCat | CostType | LessonStatus | Score
Not started | Initiating | Risk | Avoid | Open | Green | Must | Functional | Proposed | Unaware | Pending | Start | Yes | Predictive | Small | Labor | Labor | Open | 1
In progress | Planning | Assumption | Mitigate | Closed | Amber | Should | Non-functional | Approved | Resistant | Approved | Stop | No | Agile | Medium | Vendors & contractors | Non-labor | Actioned | 2
Complete | Executing | Issue | Transfer |  | Red | Could | Constraint | In progress | Neutral | Rejected | Continue |  | Hybrid | Large | Software & licenses | Reserve | Closed | 3
Blocked | Monitoring & Controlling | Dependency | Accept |  |  | Won't | Transition | Done | Supportive | Deferred |  |  |  |  | Hardware |  |  | 4
On hold | Closing |  | Escalate |  |  |  |  | Accepted | Leading | [5 empty] | Training & change |  |  | 5
|  |  | Exploit |  |  |  |  | Deferred | [6 empty] | Travel & other
|  |  | Enhance |  |  |  |  | Rejected | [6 empty] | Contingency reserve