EXAMPLE T02  ·  PROJECT MANAGER IN A BOX

# Project Charter

Formally authorizes the project and gives the PM authority to use organizational resources.

Example based on the fictional Project Beacon. Names, figures and outcomes are invented for illustration. This is a filled-in example of template T02. Use the blank template to start your own.

| Project name | Project Beacon – Volunteer & Donor Portal |
| --- | --- |
| Project ID | PB-2026-01 |
| Sponsor | Dana Ruiz, Executive Director |
| Project manager | Marcus Lee |
| Product owner / business owner | Priya Shah, Volunteer Programs Manager |
| Version / date | v1.0, January 9, 2026 |

## 1. Project summary

Northside Food Collective runs volunteer shifts and recurring gifts on spreadsheets and paper forms. Staff spend about 22 hours a week on scheduling, volunteer records are duplicated or incomplete, and donors cannot manage their own gifts. Project Beacon will replace these with a secure online portal connected to the existing donor CRM, so volunteers and donors manage their own participation and staff time moves to supporting them. The business case estimates a saving of about 14 staff hours a week (decision DEC-001).

## 2. Goals and success criteria

| Goal / measure | Baseline | Target | Measured by / when |
| --- | --- | --- | --- |
| Volunteer shifts booked online | 0% | 80% of shifts | Portal reports |
| Staff hours spent on scheduling | 22 hrs/week | 8 hrs/week or less | Time study |
| Recurring donors | 310 | 400 by October 2026 | Donor CRM |
| Admin accounts using MFA | 0% | 100% at go-live | Identity provider report |

## 3. Scope

| In scope | Volunteer sign-up with MFA; viewing, booking and cancelling shifts; recurring shifts with capacity limits; hours logging and a downloadable certificate; donor recurring gifts through a PCI-compliant processor; nightly sync with the donor CRM; migration of volunteer records from spreadsheets; training for staff and volunteers; two weeks of hypercare after go-live. |
| --- | --- |
| Out of scope (explicit) | Event and gala ticketing; text-message reminders (revisit after go-live); replacing the donor CRM; native mobile apps (the portal must work in mobile browsers). |
| Key deliverables | Live portal; migrated and cleaned data; security test report; training materials; closeout report. |

## 4. Milestones (high level)

| Milestone | Target date | Gate / approval needed? |
| --- | --- | --- |
| Charter signed | Jan 9, 2026 | Yes: sponsor |
| Plan and baselines approved | Feb 6, 2026 | Yes: sponsor (planning gate) |
| MVP pilot with 20 volunteers | Mar 27, 2026 | No |
| Go-live readiness and CAB approval | May 26, 2026 | Yes: CAB |
| Go-live | Jun 1, 2026 | Yes: sponsor go/no-go |
| Closeout report and retrospective | Jun 26, 2026 | Yes: sponsor |

## 5. Budget and resources

| Approved budget (incl. reserve) | $185,000, including a $17,000 contingency reserve (about 10%) |
| --- | --- |
| Funding source | Technology grant; any balance from the operating budget |
| Core team / roles | PM, Product Owner, Business Analyst, Technical Lead (vendor), Security Lead, Finance Partner, Donor Relations Lead |
| Vendors | Build vendor, to be chosen by competitive bid (target January 30); third-party penetration tester |

## 6. Delivery approach

| Approach (predictive / agile / hybrid) and why | Hybrid. A fixed milestone plan and budget, built in two-week sprints. The grant deadline is fixed, but portal features will be shaped by volunteer feedback. To be confirmed at the planning gate using the Delivery Approach worksheet (T04). |
| --- | --- |
| Project size (Small / Medium / Large) | Medium |
| Required review gates (e.g., architecture, security, CAB) | Security requirements review before build; penetration test before UAT; CAB approval before go-live |

## 7. Key risks, assumptions and constraints

| Type | Description | Owner |
| --- | --- | --- |
| Risk | Because many volunteers are used to paper sign-ups, adoption may lag, reducing the staff-time savings. | Priya Shah |
| Assumption | At least 90% of volunteers have a phone that can run an authenticator or receive SMS codes. | Aisha Grant |
| Constraint | The grant requires the project to finish by June 26, 2026. | Dana Ruiz |

## 8. Governance and PM authority

| Steering / decision forum | Steering committee (Dana Ruiz, Aisha Grant, Kevin O’Neil, Priya Shah, Marcus Lee), monthly |
| --- | --- |
| PM can approve changes up to | $1,000 and no change to any milestone date. Sponsor: up to $25,000 or 15 days. Above that: steering committee. |
| Escalation path | PM, then Sponsor (within 2 working days), then Board Technology Committee |
| Reporting cadence | Weekly status report to the Sponsor (Mondays); monthly steering pack; monthly one-page memo to the Board Technology Committee |

## 9. Stakeholders

Key groups are the Board Technology Committee, pantry site coordinators, about 1,200 volunteers, Donor Relations, IT and Security, Finance, and the build vendor. The full list, scores and engagement plan are in the Stakeholder Register (T03).

## 10. Approval

| Role | Name | Signature / approval method | Date |
| --- | --- | --- | --- |
| Sponsor | Dana Ruiz | Email approval | Jan 9, 2026 |
| Project Manager | Marcus Lee | Email approval | Jan 9, 2026 |
| Product Owner | Priya Shah | Email approval | Jan 9, 2026 |