EXAMPLE T15  ·  PROJECT MANAGER IN A BOX

# Status Report

A one-page weekly update: overall RAG, progress, next steps, top risks and decisions needed.

Example based on the fictional Project Beacon. Names, figures and outcomes are invented for illustration. This is a filled-in example of template T15. Use the blank template to start your own.

| Project | Project Beacon – Volunteer & Donor Portal |
| --- | --- |
| Report date | June 22, 2026 (final report) |
| Project manager | Marcus Lee |
| Overall status (Green / Amber / Red) | Green |

## Summary

Project Beacon is complete. The portal went live on June 1, 2026, the committed date, and the sponsor approved closeout today. Final cost is $169,400 against $185,000 approved. Adoption is still ramping (61% of shifts booked online against an 80% target), so three follow-up items now belong to the business owners.

## Decisions / help needed

| Ask | Owner | Needed by |
| --- | --- | --- |
| Decide phase 2 scope and funding (gala ticketing, text reminders) | Dana Ruiz | Jul 31, 2026 |
| Re-measure adoption targets and report to the sponsor | Priya Shah | Oct 30, 2026 |
| Renew the portal subscription before the first-year term ends | Kevin O’Neil | May 31, 2027 |

## Health by area

| Area | Status | Comment |
| --- | --- | --- |
| Schedule | Green | 100% complete vs 100% planned (SPI 1.00). Go-live June 1 as committed; closed June 22, four days before the grant deadline. |
| Budget | Green | Final cost $169,400 vs $185,000 approved (8.4% under). All lines closed; $15,000 of the reserve was not needed. |
| Scope | Green | All 9 committed requirements accepted. R-10 (text reminders) and gala ticketing deferred to phase 2. |
| Risk | Green | No open Red items. Three follow-up risks (one Amber, two Green) handed to business owners. |
| Quality | Green | No open Severity 1 or 2 defects. Hypercare ended June 12 with no Severity 1 or 2 incidents. |
| Stakeholders | Green | 9 of 10 stakeholders at their desired engagement. Volunteers are still Neutral; the target is Supportive. |

## Completed this period

Go-live on June 1 after CAB approval on May 26; hypercare finished June 12 with no Severity 1 or 2 incidents.

Acceptance and transition sign-off (T21) signed on June 12.

Retrospective held and lessons recorded (T19); closeout report (T20) approved and records archived.

## Planned next period

Business owners take over the three open follow-up items above.

Brightline moves the portal to its standard support plan.

The project team stands down; team members return to their departments.

## Top risks and issues

| Item | Score / RAG | Response | Owner |
| --- | --- | --- | --- |
| R-007 Adoption targets not yet reached at closeout | 6 / Amber | Transfer: re-measure October 30 | Priya Shah |
| R-008 Phase 2 scope is undecided | 4 / Green | Transfer: decide by July 31 | Dana Ruiz |
| R-009 Portal subscription lapses if not renewed | 4 / Green | Transfer: renew by May 31, 2027 | Kevin O’Neil |

## Upcoming milestones

| Milestone | Baseline date | Forecast date | Status |
| --- | --- | --- | --- |
| Go-live | Jun 1, 2026 | Jun 1, 2026 | Done, on the committed date |
| Closeout approved by the sponsor | Jun 26, 2026 (grant deadline) | Jun 22, 2026 | Done, four days early |
| Adoption targets re-measured | Oct 30, 2026 | Oct 30, 2026 | Owned by Priya Shah |