EXAMPLE T20  ·  PROJECT MANAGER IN A BOX

# Closeout & Impact Report

Summarizes what was delivered, performance against baselines, benefits, lessons and open items.

Example based on the fictional Project Beacon. Names, figures and outcomes are invented for illustration. This is a filled-in example of template T20. Use the blank template to start your own.

| Project | Project Beacon – Volunteer & Donor Portal |
| --- | --- |
| Sponsor | Dana Ruiz, Executive Director |
| Project manager | Marcus Lee |
| Close date | June 22, 2026 |

## 1. Executive summary (impact)

Northside’s volunteer and donor portal went live on June 1, 2026, the committed date, and the project closed on June 22, four days before the grant deadline of June 26. Volunteers now register, book shifts and log hours online. Donors manage their own recurring gifts. Records sync nightly with the donor CRM, and every admin account uses MFA. Final cost was $169,400 against $185,000 approved. Three weeks after go-live, 61% of shifts are booked online and scheduling time has fallen from 22 to 11 hours a week. Those measures are moving the right way but will not reach target until the autumn, so they are tracked after closure. Gala ticketing and text reminders were deferred to phase 2.

## 2. Results against success criteria

| Goal / measure | Baseline | Target | Actual | Met? |
| --- | --- | --- | --- | --- |
| Volunteer shifts booked online | 0% | 80% of shifts | 61% (three weeks after go-live) | Not yet |
| Staff hours spent on scheduling | 22 hrs/week | 8 hrs/week or less | 11 hrs/week | Not yet |
| Recurring donors | 310 | 400 by October 2026 | 327 | Not yet |
| Admin accounts using MFA | 0% | 100% at go-live | 100% | Yes |

## 3. Performance against baselines

| Dimension | Baseline | Actual | Variance | Explanation |
| --- | --- | --- | --- | --- |
| Scope | 9 committed requirements (R-01 to R-09) | 9 delivered | 0 | R-10 (text reminders) and gala ticketing (CR-002) were deferred to phase 2 by sponsor decision. |
| Finish date | Go-live June 1; close by June 26, 2026 | Go-live June 1; closed June 22, 2026 | 0 days on go-live; 4 days early on closure | Sprint 4 started a week late because the CRM sandbox arrived late. The one-week buffer between the team’s plan and the committed date absorbed it. |
| Cost | $185,000 | $169,400 | $15,600 under | Planned lines cost $167,400. Two approved changes added $2,000 (CR-003, data-cleanup hours +$1,200; CR-004, analyst hours +$800), paid from the $17,000 reserve. The other $15,000 was not needed. |
| Quality | Zero critical accessibility findings; no open Severity 1 or 2 defects at go-live | Met | None | One high-severity penetration-test finding was fixed and retested before UAT. |

## 4. Methodology

Hybrid delivery: a fixed milestone plan and budget, built in five two-week sprints with a sprint review at the end of each. Gates were the planning gate, the penetration test before UAT, and CAB approval before go-live. Medium-size tailoring: a scored RAID log reviewed every two weeks, a change request form with the sponsor approving above $1,000, and no quantitative risk analysis.

## 5. What worked and lessons learned

Hold requirements sessions where users work. Workshops at pantry sites found needs that office meetings missed. Recommendation: make on-site sessions the default for user-facing projects (L-01).

Check source data early. The data-quality problem was assumed, not tested, and blocked migration for two weeks. Recommendation: profile source data during Planning and add the task to the WBS template (L-02).

Keep the vendor in every ceremony. Sprint reviews with the vendor kept progress visible. Recommendation: write vendor attendance into the statement of work (L-03).

Name third-party access in the contract. The CRM sandbox arrived 8 working days late. Recommendation: list needed-by dates for outside access in the SOW and ask for it at kickoff (L-04).

Keep a buffer between the team’s plan and any date promised outside the team. It absorbed the Sprint 4 slip (L-05).

Set adoption targets after the pilot, and name the post-launch owner in the charter (L-06). The full list is in the Lessons Learned Register (T19).

## 6. Open items and handover

| Open item | New owner | Due |
| --- | --- | --- |
| Re-measure shift-booking and scheduling-hours targets and the recurring-donor count | Priya Shah | Oct 30, 2026 |
| Decide phase 2 scope (gala ticketing, text reminders) | Dana Ruiz | Jul 31, 2026 |
| Renew the portal platform subscription | Kevin O’Neil | May 31, 2027 |

## 7. Benefits still to be realized

Staff-time savings (target 8 hours a week or less), 80% of shifts booked online, and 400 recurring donors by October 2026. Priya Shah and Rosa Delgado measure them and report to Dana Ruiz in November 2026.

## 8. Project documentation

The project repository (folders 00-Admin to 05-Closing), the vendor contract and the Project Workbook are archived in the Northside shared drive under Project Beacon, retained under the organization’s records policy.

## 9. Approval to close

| Role | Name | Signature / approval method | Date |
| --- | --- | --- | --- |
| Sponsor | Dana Ruiz | Email approval | Jun 22, 2026 |
| Project Manager | Marcus Lee | Email approval | Jun 22, 2026 |