EXAMPLE T21  ·  PROJECT MANAGER IN A BOX

# Acceptance & Transition Sign-off

Records formal acceptance of deliverables and the handover to operations or the business owner.

Example based on the fictional Project Beacon. Names, figures and outcomes are invented for illustration. This is a filled-in example of template T21. Use the blank template to start your own.

| Project | Project Beacon – Volunteer & Donor Portal |
| --- | --- |
| Release / phase | Release 1.0 (live June 1, 2026): transfer to operations |
| Receiving owner (operations / business) | Priya Shah (business) and Aisha Grant (IT support) |
| Date | June 12, 2026 |

## 1. Deliverables accepted

| Deliverable | Acceptance evidence | Accepted by | Date |
| --- | --- | --- | --- |
| Live portal: sign-up with MFA, shift booking, hours logging and certificates, recurring gifts | UAT passed May 22; all 9 committed requirements (R-01 to R-09) accepted; five sprint reviews minuted | Priya Shah | Jun 12, 2026 |
| Nightly CRM sync | 14 consecutive nights with no unresolved sync errors | Rosa Delgado | Jun 12, 2026 |
| Migrated volunteer data | Reconciliation: 1,196 of 1,200 active volunteer records matched; the other 4 fixed by hand | Priya Shah | Jun 12, 2026 |
| Security test report | Third-party penetration test report; one high finding fixed and retested before UAT began May 11 | Aisha Grant | Jun 12, 2026 |
| Training sessions and materials | Eight sessions delivered May 26 to 29; attendance recorded | Priya Shah | Jun 12, 2026 |

## 2. Operational readiness

☑  Support model agreed (who, hours, escalation)

☑  Documentation and runbooks handed over

☑  Users and support staff trained

☑  Access transferred; project-only access removed

☑  Monitoring and alerting in place (Technical)

☑  Backup / recovery tested (Technical)

☑  Known defects and workarounds documented

## 3. Hypercare / warranty

| Period | June 1 to June 12, 2026 (two weeks) |
| --- | --- |
| Exit criteria | No Severity 1 or 2 incident open for 5 working days; fewer than 5 support tickets a day for the last 3 days; handover meeting held |
| Contact during hypercare | Tom Becker (Brightline), then Marcus Lee |

## 4. Exceptions

Text-message reminders (R-10) were not built. Deferred to phase 2. Owner: Dana Ruiz, decision by July 31, 2026.

Adoption targets not yet met (61% of shifts booked online against 80%). Owner: Priya Shah, re-measure October 30, 2026.

Two minor wording defects (Severity 4) on the certificate page. Workaround documented; Brightline fixes them in the first support release in July 2026.

## 5. Sign-off

| Role | Name | Signature / approval | Date |
| --- | --- | --- | --- |
| Sponsor | Dana Ruiz | Email approval | Jun 12, 2026 |
| Receiving owner | Priya Shah | Email approval | Jun 12, 2026 |
| Project Manager | Marcus Lee | Email approval | Jun 12, 2026 |